## Zone 1
Controller A | Station | Repairs Needed | Dates
| 1 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve boxes. | 2025-02-25
| 2 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-02-25
| 3 | Replace 2 broken nozzles. | 2025-02-25
| 4 | Replace 1 Broken nozzle. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above plant material. Taller pop-up sprinkler head need to be installed | 2025-02-25
5
| 6 | Add 1 sprinkler head. Replace 1 broken nozzle. | 2025-02-25
| 7 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve boxes. | 2025-02-25
| 8 | Cancel (2) sprinklers, move (1) sprinkler and add (2) sprinklers for best coverage. | 2025-03-04
| 9 | Replace 1 square broken valve box. Add drip system and emitter for (27) plants (1) tree. | 2/25/2025 3/4/2025
| 10 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve boxes. | 2025-02-25
11
| 12 | Replace malfunctioning solenoid. Replace malfunctioning decoder. | 12/19/2024 2/24/2025
| 13 | Replace malfunctioning decoder. | 2025-02-24
14
| 15 | Replace 1 broken nozzle. | 2025-02-25
16
17
18
19
20
| 21 | Straighten, raise, and/or move 1 sprinkler head to proper grade. | 2025-02-25
22
23
24
| 25 | Replace 1 broken nozzle. | 2025-02-25
| 26 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
| 27 | Replace 1 broken nozzle. | 2025-02-25
| 28 | Straighten, raise, and/or move 2 sprinkler head to proper grade. | 2025-02-25
29
30
31
32
| 33 | Replace 1 square broken valve box. | 2025-02-25
34
| 35 | Rotor is not rotating and needs to be replaced. Replace 1 broken nozzle. Replace 1 square broken valve box. | 2025-02-25
36
| 37 | Rotor is not rotating and needs to be replaced. | 2025-02-25
38
39
| 40 | Replace 2 square broken valve boxes. Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
41
| 42 | Straighten, raise, and/or move 1 sprinkler head to proper grade. Replace 1 broken nozzle. | 2025-02-25
| 43 | Rotor is not rotating and needs to be replaced. Add 1 sprinkler head. | 2025-02-25
44
| 45 | Add 1 sprinkler head. | 2025-02-25
46
| 47 | Replace decoder for this station Repair broken lateral line | 7/2/2025 7/10/2025
| 48 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve boxes. Replace decoder for this station | 2/25/2025 7/2/2025
| 49 | Replace 1 leaking sprinkler head. Replace decoder for this station | 2/25/2025 7/2/2025
50
51
52
53
| 54 | Straighten, raise, and/or move 1 sprinkler head to proper grade. | 2025-02-25
55
| 56 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-02-25
| 57 | Repair 1 broken drip tubing, replace 1 leaking Netafim indicator | 2025-07-02
58
| 59 | Replace 5 broken nozzles. Add 1 sprinkler head. | 2025-02-25
| 60 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-02-25
61
| 62 | Replace 5 broken nozzles. Replace 1 leaking sprinkler head. | 2025-02-25
63
| 64 | Repair 1 broken lateral line in root infested area. Straighten, raise and/or move 2 sprinkler heads to proper grade. Replace 1 leaking sprinkler head. | 2025-02-25
| 65 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Repair 1 broken lateral line under the sidewalk | 2/25/2025 7/21/2025
| 66 | Replace 1 broken nozzle. Move 1 sprinkler head. | 2025-02-25
67
68
69
| 70 | Repair 1 broken lateral line. | 2025-02-25
71
| 72 | Replace2 broken nozzles. | 2025-02-25
| 73 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-02-25
74
| 75 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-02-25
| 76 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-02-25
77
| 78 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Repair 2 broken Netafim lines Eliminate excessive Netafim lines to avoid water running to the tennis courts Repair 1 broken Netafim line by the clubhouse | 2/25/2025 7/2/2025 7/21/2025 7/29/2025
| 79 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Repair 2 Netafim lines at the clubhouse | 2/25/2025 7/2/2025
80
| 81 | Rotor is not rotating and needs to be replaced | 2025-02-25
| 82 | Replace broken fitting below 1 sprinkler head. | 2025-02-25
83
84
| 85 | Replace 2 broken nozzles. | 2025-02-25
| 86 | Replace 1 square broken valve box. | 2025-02-25
| 87 | Repair 1 broken lateral line. Add 1 sprinkler head. Replace 1 broken nozzle. | 2025-02-25
| 88 | Straighten, raise, and/or move 1 sprinkler head to proper grade. Replace 2 broken nozzles. | 2025-02-25
| 89 | Straighten, raise, and/or move 1 sprinkler head to proper grade. | 2025-02-25
90
91
| 92 | Repair 1 broken lateral line in root infested area. | 2025-02-25
93
| 94 | Replace 2 broken nozzles. | 2025-02-25

## Zone 2
Controller B | Station | Repairs Needed | Date
| 1 | Replace 1 square broken valve box. Cancel (1) sprinkler, move (2) sprinklers and replace (2) sprinklers. | 2/25/2025 3/4/2025
| 2 | Add drip emitters for (25) plants. | 2025-03-04
3
| 4 | Add 1 sprinkler head in root infested area. Replace 3 broken nozzles. | 2025-02-25
5
| 6 | Repair 1 broken lateral line in front of the tree | 2025-07-21
| 7 | Replace 1 leaking sprinkler head in root infested area. | 2025-02-25
8
9
10
11
12
| 13 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
| 14 | Repair 1 broken lateral line. Repair 1 broken Netafim line | 2/25/2025 7/29/2025
| 15 | Add 1 sprinkler head in root infested area. | 2025-02-25
16
17
18
19
20
21
22
23
24
25
| 26 | Replace 1 old malfunctioning solenoid | 2025-07-21
27
| 28 | Move sprinkler heads. | 2025-02-25
29
| 30 | Replace 2 broken nozzles. | 2025-02-25
| 31 | Add 1 sprinkler head in root infested area. Repair 1 broken lateral line | 2/25/2025 7/11/2025
| 32 | Replace 1 broken nozzle. | 2025-02-25
33
34
| 35 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
| 36 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 1 broken Netafim line by 1338 Commons | 2/25/2025 7/22/2025
| 37 | Repair 1 square broken valve box. | 2025-02-25
38
39
| 40 | Replace 1 leaking sprinkler head. | 2025-02-25
41
42
| 43 | Add 1 sprinkler head in root infested area. | 2025-02-25
44
45
| 46 | Repair 1 broken lateral line in root infested area. | 2025-02-25
| 47 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
| 48 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-02-25
49
| 50 | Add 1 sprinkler head in root infested area. | 2025-02-25
| 51 | Add 1 sprinkler head in root infested area. Replace 1 leaking sprinkler head. Replace 2 broken nozzles. | 2025-02-25
| 52 | Replace 2 leaking sprinkler heads. Replace 1 broken nozzle. | 2025-02-25
| 53 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-02-25
| 54 | Add 2 sprinkler heads. | 2025-02-25
| 55 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-02-25
| 56 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
57
| 58 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
| 59 | Replace 1 square broken valve box. | 2025-02-25
60
61
| 62 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 2 square broken valve boxes. | 2025-02-25
| 63 | Replace 1 square broken valve box. | 2025-02-25
| 64 | Replace 1 leaking sprinkler head. | 2025-02-25
| 65 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-02-25
66
| 67 | Replace 1 broken nozzle. Replace 3 MP Rotary nozzles that are not rotating Replace damaged old valve in the turf area and 10 sprinklers to improve pressure | 2/25/2025 7/21/2025 8/6/2025
68
69
| 70 | Replace 1 square broken valve box. | 2025-02-25
| 71 | Repair broken drip line near the garage | 2025-05-13
72
73

## Zone 3
Controller C | Station | Repairs Needed | Date
1
2
| 3 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
4
| 5 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
6
7
| 8 | Replace 1 broken valve box in root infested area | 2025-03-05
9
| 10 | Replace 3 broken nozzles. Rotor is not rotating and needs to be replaced. | 2025-03-05
| 11 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 12 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 13 | Replace 1 malfunctioning solenoid that is stuck closed | 2025-07-21
| 14 | Move 1 sprinkler head. | 2025-03-05
15
| 16 | Add 1 sprinkler head in root infested area. Replace 3 broken nozzles. Replace broken fitting below 1 sprinkler head. | 2025-03-05
| 17 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 18 | Replace (1) malfunctioning solenoid (903 Dunbarton). Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 3/3/2025 3/5/2025
| 19 | Add 1 sprinkler head . Replace broken fitting below 1 sprinkler head. Replace 1 broken nozzle. | 2025-03-05
| 20 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
21
22
23
24
25
| 26 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
27
| 28 | Straighten, raise and/or move 1 sprinkler head to proper grade. | 2025-03-05
| 29 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 30 | Move (2) sprinklers closer to the grass for best coverage | 2025-03-04
| 31 | Add emitters for (22) plats and (2) trees. | 2025-03-04
32
| 33 | Replace 2 broken nozzles. | 2025-03-05
| 34 | Repair 1 broken Netafim line, repair several Netafim lines - damaged from stump grinder | 2025-07-02
| 35 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-03-05
| 36 | Straighten, raise and/or move 1 sprinkler head to proper grade. Replace 2 sprinkler head. The existing sprinkler head is/are not tall enough to spray above plant material. Taller pop-up sprinkler head need to be installed. Replace broken fitting below 1 sprinkler head. Repair 1 broken lateral line close to the tree in a root infested area | 3/5/2025 7/2/2025
| 37 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
38
| 39 | Repair 2 sprinkler heads. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 2025-03-05
| 40 | Rotor is not rotating and needs to be replaced. | 2025-03-05
| 41 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-03-05
| 42 | Rotor is not rotating and needs to be replaced. Straighten, raise and/or move 1 sprinkler head to proper grade. | 2025-03-05
| 43 | Repair 1 broken lateral line in root infested area. Replace 1 square broken valve box. | 2025-03-05
44
| 45 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 46 | Rotor is not rotating and needs to be replaced. Replace 1 broken rotor in root infested area near 411 Dunbarton | 3/5/2025 7/2/2025
| 47 | Rotor is not rotating and needs to be replaced. | 2025-03-05
| 48 | Replace 2 broken nozzles. | 2025-03-05
49
50
| 51 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 52 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 53 | Replace 1 square broken valve box. | 2025-03-05
54
55
56
57
58
| 59 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 60 | Move 1 sprinkler head. | 2025-03-05
| 61 | Move 1 sprinkler head. | 2025-03-05
| 62 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
63
| 64 | Replace 1 leaking sprinkler head. Repair 3 sprinkler heads. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 2025-03-05
| 65 | Replace (1) malfunctioning solenoid (2330 Dunbarton). Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 3/3/2025 3/5/2025
| 66 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 2 square broken valve boxes. | 2025-03-05
| 67 | Repair 1 broken lateral line in root infested area, move 1 sprinkler closer to sidewalk for better coverage | 2025-07-02
| 68 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve box. | 2025-03-05
| 69 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 2 square broken valve boxes. | 2025-03-05
70
| 71 | Replace 2 broken nozzles. | 2025-03-05
72
73
74
| 75 | Replace (1) malfunctioning solenoid (1333 Commons) Replace 1 leaking sprinkler head. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 3/3/2025 3/5/2025
76
77
| 78 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-05
| 79 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace 1 square broken valve box. Repair 1 broken Netafim line | 3/5/2025 7/2/2025
| 80 | Repair 1 broken fitting | 2025-07-02

## Zone 4
Controller D | Station | Repairs Needed | Dates
| 1 | Repair broken root infested lateral line near the large tree in front of 214 Dunbarton Circle | 2025-05-13
| 2 | Replace 1 broken nozzle. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above plant material. Taller pop up sprinkler head need to be installed. | 2025-03-07
3
4
| 5 | Add 1 sprinkler head in root infested area. | 2025-03-07
6
| 7 | Replace 1 square broken valve box(es). | 2025-03-07
8
9
| 10 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 1 broken drip line by 104 Dunbarton | 3/7/2025 7/30/2025
11
| 12 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
| 13 | Repair 1 broken lateral line in root infested area. Add 1 sprinkler head in root infested area. | 2025-03-07
14
15
16
| 17 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
18
| 19 | Replace 1 broken nozzle. | 2025-03-07
20
| 21 | Add 1 sprinkler head in root infested area. Replace 2 broken nozzles. | 2025-03-07
| 22 | Replace broken fitting below 1 sprinkler head in root infested area. Repair 1 broken Netafim line | 3/7/2025 7/2/2025
23
| 24 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
| 25 | Replace 1 broken nozzle. Install an additional sprinkler for improved water coverage where the turf is declining | 3/7/2025 6/3/2025
26
27
| 28 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
| 29 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
30
| 31 | Repair 1 broken lateral line in root infested area.
32
33
| 34 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 1 broken lateral line in root infested area | 3/7/2025 7/2/2025
| 35 | Replace 1 leaking sprinkler head. Replace 1 broken nozzle.
| 36 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
37
| 38 | Add 1 sprinkler head in root infested area. Replace 2 broken nozzles. | 2025-03-07
| 39 | Replace 4 broken nozzles. Replace broken fitting below 1 sprinkler head. | 2025-03-07
40
| 41 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
42
43
| 44 | Replace 3 leaking sprinkler heads. | 2025-03-07
| 45 | Add 3 sprinkler heads in root infested areas. Replace 1 leaking sprinkler head. Replace 1 broken nozzle. | 2025-03-07
46
| 47 | Add 1 sprinkler head in root infested area. Replace 1 broken nozzle. | 2025-03-07
48
| 49 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
| 50 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 1 broken Netafim line | 3/7/2025 7/2/2025
51
| 52 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-07
| 53 | Replace 1 broken sprinkler. Move 1 sprinkler head. Replace 2 rotary for U Series Nozzles to improve water coverage where the turf and shrub are declining | 3/7/2025 6/3/2025
| 54 | Replace 3 broken nozzles. Replace 3 leaking sprinkler heads. | 2025-03-07

## Zone 5
Controller E | Station | Repairs Needed | Dates
| 1 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
| 2 | Replace 1 broken nozzle. Replace 1 broken sprinkler at 1045 Vanderbilt | 3/13/2025 7/2/2025
| 3 | Straighten, raise, and/or move 1 sprinkler head to proper grade. | 2025-03-13
4
| 5 | Replace 5 broken nozzles. Replace 1 leaking sprinkler head. Replace 5 broken nozzles. | 2025-03-13
6
7
8
9
10
| 11 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
| 12 | Repair 1 broken lateral line in root infested area.
| 13 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
| 14 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
| 15 | Replace 1 broken sprinkler. Add 1 sprinkler head. Replace 2 broken nozzles. | 2025-03-13
| 16 | Replace broken fitting below 1 sprinkler head. Repair 3 broken drip lines | 3/13/2025 7/2/2025
17
| 18 | Rotor is not rotating and needs to be replaced. | 2025-03-13
| 19 | Add 1 sprinkler head in root infested area. Replace 1 broken nozzle | 2025-03-13
| 20 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
21
| 22 | Add 1 sprinkler head in root infested area. Replace 1 broken nozzle | 2025-03-13
| 23 | Replace 1 broken nozzle. | 2025-03-13
| 24 | 1083 Elmhurst - Replace (1) malfunctioning solenoid. Repair 1 broken drip line Repair 1 broken lateral line in front of the tree by 201 Elmhurst | 3/10/2025 7/2/2025 7/22/2025
| 25 | Move 1 sprinkler head. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 26 | Add 2 sprinkler heads. Replace 2 broken nozzles. | 2025-03-13
27
| 28 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
29
| 30 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). Move 1 sprinkler head. Rotor is not rotating and needs to be replaced. | 2025-03-13
| 31 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). Replace square broken valve box(es) Replace broken rotor damaged by Rodents. | 3/13/2025 4/24/2025
| 32 | Move 1 sprinkler head. Replace 2 broken nozzles. | 2025-03-13
| 33 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 34 | Replace 1 broken nozzle. Replace 1 broken sprinkler. Repair 1 broken lateral line | 3/13/2025 7/29/2025
35
| 36 | Replace 1 leaking sprinkler head. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. Replace 1 malfunctioning solenoid by 1305 Vanderbilt | 3/13/2025 7/30/2025
| 37 | Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. Replace broken fitting below 1 sprinkler head in root infested area. | 2025-03-13
| 38 | Replace broken fitting below 2 sprinkler heads. | 2025-03-13
| 39 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 40 | Add 1 sprinkler head in root infested area. Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 41 | Repair 1 broken lateral line in root infested area. Add 1 sprinkler head. Move 1 sprinkler head. Replace 2 broken nozzles. | 2025-03-13
| 42 | Replace broken fitting below 1 sprinkler head in root infested area. Repair 1 broken fitting in root infested area | 3/13/2025 7/2/2025
| 43 | Add 1 sprinkler head in root infested area. | 2025-03-13
44
45
46
47
48
49
50
| 51 | Replace broken fitting below 1 sprinkler head. Repair 1 broken Netafim line Repair 1 broken Netafim line | 3/13/2025 7/2/2025 7/21/2025
| 52 | Replace 1 broken nozzle. | 2025-03-13
| 53 | Replace 1 broken sprinkler. Replace 6 broken nozzles. | 2025-03-13
54
| 55 | Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. Replace 1 broken nozzle. | 2025-03-13
| 56 | Replace 3 broken nozzles. | 2025-03-13
| 57 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair broken lateral lines in root infested area | 3/13/2025 7/2/2025
| 58 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
59
60
| 61 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 62 | 603 Elmhurst - Replace (1) malfunctioning solenoid Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 1 broken Netafim line by 603 Elmhurst | 3/10/2025 3/13/2025 7/22/2025
| 63 | Replace 1 leaking sprinkler head. Repair 1 broken Netafim line | 3/13/2025 7/2/2025
| 64 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 4 broken drip lines | 3/13/2025 7/2/2025
| 65 | Repair and relocate (1) broken lateral line in root infested area. Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 3/4/2025 3/13/2025
| 66 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair 1 broken lateral line. Replace damaged decoder | 3/13/2025 7/2/2025
| 67 | Replace 1 leaking sprinkler head. | 2025-03-13
| 68 | Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 69 | Replace 1 leaking sprinkler head. | 2025-03-13
| 70 | Replace 2 broken nozzles. Replace 1 weeping valve | 3/13/2025 5/16/2025
| 71 | Replace 1 leaking sprinkler head. | 2025-03-13
| 72 | Replace broken fitting below 1 sprinkler head. Replace 1 broken nozzle. | 2025-03-13
| 73 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 74 | Repair 1 broken lateral line by the tree and eliminate excessive line of Netafim | 2025-07-02
| 75 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 76 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Repair broken root infested lateral line beneath a tree near 707 Elmhurst Circle | 3/13/2025 5/1/2025
77
| 78 | Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 79 | Replace 2 broken nozzles. | 2025-03-13
| 80 | Repair 1 broken drip line | 2025-07-02
| 81 | Repair 1 broken drip line in a root infested area | 2025-07-21
| 82 | Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 83 | Replace 2 broken nozzles. | 2025-03-13
| 84 | Replace 1 leaking sprinkler head. Replace 2 broken nozzles. | 2025-03-13
| 85 | Repair 1 broken lateral line in root infested area. Replace 1 leaking sprinkler head. Replace 1 broken nozzles. | 2025-03-13
86
| 87 | Repair drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
88
89
90
| 91 | Replace broken fitting below 1 sprinkler head in root infested area. | 2025-03-13
| 92 | Repair 1 broken lateral line in root infested area. Repair 1 broken lateral line behind the tree | 3/13/2025 7/2/2025

## Zone 6
Controller F | Station | Repairs Needed | Dates
1
| 2 | Replace 1 leaking sprinkler head. | 2025-03-13
| 3 | Replace 1 leaking sprinkler head. | 2025-03-13
4
| 5 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
6
| 7 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
8
9
| 10 | Repair 2 broken lateral lines in root infested area. Repair broken Netafim lines damaged by cable box construction. | 3/13/2025 4/29/2025
| 11 | Replace 1 leaking sprinkler head. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plank material. Taller pop-up sprinkler head need to be installed. Move 1 sprinkler head. Replace 1 broken nozzle. | 2025-03-13
| 12 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 13 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
14
| 15 | Replace 1 leaking sprinkler head. | 2025-03-13
| 16 | Move 1 sprinkler head. Add 1 sprinkler head. Straighten, raise and/or move 1 sprinkler head to proper grade. Replace 1 broken nozzle. | 2025-03-13
| 17 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 18 |  | 2025-03-13
| 19 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 20 | Straighten, raise and/or move 1 sprinkler head to proper grade. Replace 1 broken nozzle. | 2025-03-13
21
| 22 | Move 1 sprinkler head. Repair 1 broken lateral line in root infested area. | 2025-03-13
23
| 24 | 618 Elmhurst - Emergency water main line break | 2025-07-02
25
| 26 | Straighten, raise and/or move 2 sprinkler heads to proper grade. Replace broken fitting below 1 sprinkler head. | 2025-03-13
| 27 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 28 | Replace malfunctioning solenoid by 606 Elmhurst Repair 1 broken fitting by 604 Elmhurst | 3/14/2025 7/30/2025
| 29 | Move 1 sprinkler head. Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
30
| 31 | Replace 2 broken nozzles. Replace 2 leaking sprinkler heads. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
32
| 33 | Replace 2 broken nozzles. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 34 | Add 1 sprinkler head. Replace 4 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 35 | Replace 1 leaking sprinkler head. Replace 1 broken nozzle | 2025-03-13
36
| 37 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
38
| 39 | Replace 1 leaking sprinkler head. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 40 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
41
42
43
| 44 | Add 1 sprinkler head in root infested area. Move 1 sprinkler head. Replace broken fitting below 1 sprinkler head in root infested area. | 2025-03-13
| 45 | Replace 2 leaking sprinkler heads. | 2025-03-13
46
| 47 | Replace 1 square broken valve box(es). Repair 3 broken drip lines Repair broken drip | 3/13/2025 7/2/2025 7/7/2025
48
49
| 50 | Add 1 sprinkler head. Replace 1 broken sprinkler. Replace 1 broken nozzle. | 2025-03-13
| 51 | Replace 1 leaking sprinkler head. | 2025-03-13
| 52 | Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 53 | Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. Add 1 sprinkler head. Replace 1 square broken valve box(es). | 2025-03-13
| 54 | Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
55
56
57
58
59
60
61
| 62 | Add 1 sprinkler head in root infested area. | 2025-03-13
63
| 64 | Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. Add 1 sprinkler head. | 2025-03-13
| 65 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. Replace 1 square broken valve box(es). | 2025-03-13
| 66 | Add 1 sprinkler head. | 2025-03-13
67
| 68 | Add 1 sprinkler head. | 2025-03-13
| 69 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 70 | Repair 1 broken lateral line. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
71
| 72 | Repair 1 broken later line in root infested area. | 2025-03-13
| 73 | Replace 2 sprinkler heads. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. | 2025-03-13
| 74 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
| 75 | Replace 1 broken nozzle. Replace 1 leaking sprinkler head. | 2025-03-13
| 76 | Repair 1 broken lateral line. Add 2 sprinkler heads. Replace 1 sprinkler head. The existing sprinkler head is/are not tall enough to spray above the plant material. Taller pop-up sprinkler head need to be installed. Replace 1 broken nozzle. | 2025-03-13
77
| 78 | Straighten raise and/or move 1 sprinkler head to proper grade. Add 1 sprinkler head. | 2025-03-13
| 79 | straighten raise and/or move 1 sprinkler head to proper grade. Add 1 sprinkler head. | 2025-03-13
80
81
| 82 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-13
|  | No station stated: Zone - Repair 2 damaged irrigation wires that were causing an electrical sort to the irrigation. Confirm the controller is in good working order and has no other issues | 2025-07-02

## Zone 7
Controller G | Station | Repairs Needed | Dates
1
| 2 | Replace broken fitting below 2 sprinkler heads. | 2025-03-17
| 3 | Straighten, raise, and/or move 1 sprinkler head to proper grade. | 2025-03-17
| 4 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
| 5 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
| 6 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Repair 1 broken Netafim line Repair 2 broken Netafim lines by 1497 University | 3/17/2025 7/2/2025 7/22/2025
7
8
9
10
| 11 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
| 12 | Add 1 sprinkler head. | 2025-03-17
13
14
15
16
| 17 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Replace broken fitting below 1 sprinkler head. Replace square broken valve box. Repair 1 broken lateral line in a root infested area | 3/17/2025 7/29/2025
| 18 | Replace 1 leaking sprinkler head.
19
| 20 | Replace 1 broken lateral line in root infested area. Replace 1 broken nozzle. | 2025-03-17
21
| 22 | Replace 1 broken lateral line. Straighten, raise, and/or move 1 sprinkler head to proper grade. | 2025-03-17
23
| 24 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
25
| 26 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
27
28
| 29 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. Repair several broken Netafim lines | 3/17/2025 7/21/2025
| 30 | Replace 1 broken nozzle.
| 31 | Replace 1 sprinkler head. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 2025-03-17
32
| 33 | Replace 2 sprinkler heads. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 2025-03-17
| 34 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added.
| 35 | Repair 1 broken lateral line in root infested area. Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
36
| 37 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
| 38 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
| 39 | Replace 1 sprinkler head. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 2025-03-17
| 40 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
41
| 42 | Repair the drip irrigation system. It has broken lines, tubing and/or more emitters need to be added. | 2025-03-17
43
| 44 | Repair 1 broken fitting in a root infested area and replace 1 leaking sprinkler | 2025-07-21
| 45 | Move 1 sprinkler head. | 2025-03-17
| 46 | Replace 1 sprinkler head. The existing sprinkler heads is/are not tall enough to spray above the plant material. Taller pop-up sprinkler heads need to be installed. | 2025-03-17
47

## Sheet1
Misc. Irrigation | Zone | Repairs Needed | Dates
| Zones 1-7 | Replace all batteries in 14 controllers and reprogram the controllers | 2025-03-04
| Zone 3 | Investigate and repair (2) wire failures in baseline system Install Netafim line. | 3/10/2025 3/4/2025
| Zone 1 | Replace (2) malfunctioning Baseline decoders that are causing electrical short to the irrigation controller. | 2025-04-24
Battery Controller A | Station 5 | Repair the drip irrigation system. It has broken lines, tubing, and/or more emitters need to be added. | 2025-03-24
| Station 9 | Replace broken fitting below 1 sprinkler head. | 2025-03-24
| Station 11 | Replace 1 square broken valve box. | 2025-03-24